## Actions
Action ID | Project ID | Project | Meeting Title | Meeting Date | Description | Owner | Due Date | Priority | Status | Completion Date | Days Overdue | Escalation Status | Created Date | Last Updated
ACT-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Complete data cleansing for source data | IT team | 2026-08-05 | Medium | Open |  |  | None | 2026-07-27 | 2026-07-29
ACT-002 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Confirm the final migration schedule | Ahmed | 2026-08-07 | Medium | Open |  |  | None | 2026-07-27 | 2026-07-29

## Decisions
Decision ID | Project ID | Project | Meeting Title | Meeting Date | Decision | Decision Date | Decision Owner | Status | Created Date | last updated
DEC-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Business team approved the new customer onboarding process | 2026-07-27 | TBD | Approved | 2026-07-27 | 2026-07-29

## Risks
Risk ID | Project ID | Project | Meeting Title | Meeting Date | Risk Description | Probability | Impact | Mitigation | Risk Owner | Status | Risk Score | Risk Rating | Last Review Date | Next Review Date | Created Date | Last Updated
RSK-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | UAT could be delayed if data cleansing is not completed on time | Medium | To be assessed | Mitigation to be defined | TBD | Open |  |  | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-29

## Issues
Issue ID | Project ID | Project | Meeting Title | Meeting Date | Issue Description | Owner | Impact | Status | Resolution | Severity | Created Date | Last Updated
ISS-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Data migration is currently delayed because the source data is not clean | TBD | Data migration delayed | Delayed | Pending Investigation | Medium | 2026-07-27 | 2026-07-29

## Result
Result from Project 01
Action
Action ID | Project ID | Project | Meeting Title | Meeting Date | Description | Owner | Due Date | Priority | Status | Completion Date | Days Overdue | Escalation Status | Created Date | Last Updated
ACT-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Complete data cleansing for source data | IT team | 2026-08-05 | Medium | Open |  |  | None | 2026-07-27 | 2026-07-29
ACT-002 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Confirm the final migration schedule | Ahmed | 2026-08-07 | Medium | Open |  |  | None | 2026-07-27 | 2026-07-29
Decisions
Decision ID | Project ID | Project | Meeting Title | Meeting Date | Decision | Decision Date | Decision Owner | Status | Created Date | last updated
DEC-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Business team approved the new customer onboarding process | 2026-07-27 | TBD | Approved | 2026-07-27 | 2026-07-29
Risk
Risk ID | Project ID | Project | Meeting Title | Meeting Date | Risk Description | Probability | Impact | Mitigation | Risk Owner | Status | Risk Score | Risk Rating | Last Review Date | Next Review Date | Created Date | Last Updated
RSK-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | UAT could be delayed if data cleansing is not completed on time | Medium | To be assessed | Mitigation to be defined | TBD | Open |  |  | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-29
Issue ID
Issue ID | Project ID | Project | Meeting Title | Meeting Date | Issue Description | Owner | Impact | Status | Resolution | Severity | Created Date | Last Updated
ISS-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Data migration is currently delayed because the source data is not clean | TBD | Data migration delayed | Delayed | Pending Investigation | Medium | 2026-07-27 | 2026-07-29