## Projects
Project ID | Project Name | Project Manager | Business Owner | Start Date | Target End Date | Budget | Overall Status | Schedule Status | Cost Status | Scope Status | Risk Status | Health Score | Health Band | Last Updated
PRJ-001 | CRM Implementation | Ahmed Khan | Sales Director | 2026-01-15 | 2026-09-30 | 2500000 | Amber | Amber | Green | Green | Amber | 68 | Amber | 2026-08-12
PRJ-002 | ERP Upgrade | Sara Malik | CFO | 2026-02-01 | 2026-11-30 | 4200000 | Green | Green | Green | Green | Green | 86 | Green | 2026-08-12
PRJ-003 | Customer Mobile App | Omar Ali | Digital Director | 2026-03-10 | 2026-08-31 | 1800000 | Red | Red | Amber | Green | Red | 42 | Red | 2026-08-12
PRJ-004 | Data Analytics Platform | Fatima Noor | CIO | 2026-04-01 | 2026-12-15 | 3200000 | Green | Green | Green | Green | Amber | 81 | Green | 2026-08-12
PRJ-005 | Infrastructure Modernization | Khalid Hassan | CTO | 2026-01-05 | 2026-10-31 | 6500000 | Amber | Amber | Amber | Green | Red | 61 | Amber | 2026-08-12

## Actions
Action ID | Project ID | Action | Owner | Due Date | Priority | Status | Escalation Required | Created Date | Last Updated
ACT-001 | PRJ-001 | Complete CRM UAT defect resolution | Ahmed Khan | 2026-08-08 | High | Overdue | Yes | 2026-07-25 | 2026-08-12
ACT-002 | PRJ-001 | Confirm production deployment plan | IT Manager | 2026-08-15 | High | In Progress | No | 2026-08-01 | 2026-08-12
ACT-003 | PRJ-002 | Finalize ERP training schedule | Sara Malik | 2026-08-20 | Medium | In Progress | No | 2026-08-05 | 2026-08-12
ACT-004 | PRJ-003 | Resolve mobile app performance defects | Development Lead | 2026-08-07 | Critical | Overdue | Yes | 2026-07-28 | 2026-08-12
ACT-005 | PRJ-003 | Obtain business approval for revised launch date | Omar Ali | 2026-08-10 | High | Overdue | Yes | 2026-08-02 | 2026-08-12
ACT-006 | PRJ-004 | Complete analytics dashboard validation | BI Lead | 2026-08-18 | Medium | In Progress | No | 2026-08-06 | 2026-08-12
ACT-007 | PRJ-005 | Confirm vendor hardware delivery commitment | Khalid Hassan | 2026-08-09 | High | Overdue | Yes | 2026-07-30 | 2026-08-12

## Risks
Risk ID | Project ID | Risk | Probability | Impact | Risk Score | Owner | Mitigation | Status | Escalation Required | Created Date | Last Updated
RSK-001 | PRJ-001 | CRM UAT defects may delay production deployment | High | High | 9 | Ahmed Khan | Daily defect triage and priority resolution with development team | Open | Yes | 2026-07-20 | 2026-08-12
RSK-002 | PRJ-002 | ERP user adoption may be lower than expected | Medium | Medium | 4 | Sara Malik | Role-based training and business champion network | Open | No | 2026-08-01 | 2026-08-12
RSK-003 | PRJ-003 | Mobile application performance issues may impact launch readiness | High | High | 9 | Development Lead | Performance testing and code optimization before release | Open | Yes | 2026-07-25 | 2026-08-12
RSK-004 | PRJ-004 | Source system data quality may affect dashboard accuracy | Medium | High | 6 | BI Lead | Data validation rules and reconciliation checks | Open | No | 2026-08-03 | 2026-08-12
RSK-005 | PRJ-005 | Hardware vendor delivery may miss the required installation window | High | High | 9 | Khalid Hassan | Expedite supplier delivery and maintain alternative vendor option | Open | Yes | 2026-07-18 | 2026-08-12
RSK-006 | PRJ-005 | Network migration could cause temporary service disruption | Medium | High | 6 | Infrastructure Manager | Staged migration with rollback plan | Open | No | 2026-08-04 | 2026-08-12
RSK-007 | PRJ-003 | Security testing may identify critical vulnerabilities before launch | High | High | 9 |  |  | Open | No | 2026-08-06 | 2026-08-12

## Issues
Issue ID | Project ID | Issue | Severity | Owner | Target Resolution Date | Status | Business Impact | Escalation Required | Created Date | Last Updated
ISS-001 | PRJ-001 | UAT defect backlog is delaying CRM deployment readiness | High | Ahmed Khan | 2026-08-14 | Open | Production deployment may slip | Yes | 2026-08-05 | 2026-08-12
ISS-002 | PRJ-002 | Training content is not yet finalized for finance users | Medium | Training Lead | 2026-08-21 | Open | User readiness may be affected | No | 2026-08-08 | 2026-08-12
ISS-003 | PRJ-003 | Mobile app response time exceeds agreed performance threshold | Critical | Development Lead | 2026-08-13 | Open | Launch readiness is at risk | Yes | 2026-08-04 | 2026-08-12
ISS-004 | PRJ-003 | Revised launch date has not yet received business approval | High | Omar Ali | 2026-08-15 | Open | Release planning and stakeholder communication are blocked | Yes | 2026-08-09 | 2026-08-12
ISS-005 | PRJ-004 | Dashboard data reconciliation shows inconsistencies in source records | Medium | BI Lead | 2026-08-20 | Open | Executive reporting accuracy may be affected | No | 2026-08-07 | 2026-08-12
ISS-006 | PRJ-005 | Vendor has not confirmed final hardware delivery date | High | Khalid Hassan | 2026-08-13 | Open | Installation schedule may slip | Yes | 2026-08-03 | 2026-08-12
ISS-007 | PRJ-002 | Critical finance integration defect remains unresolved | Critical |  | 2026-08-11 | Open | Month-end processing could be disrupted | No | 2026-08-06 | 2026-08-12

## Milestones
Milestone ID | Project ID | Milestone | Planned Date | Forecast Date | Actual Date | Status | Critical Milestone | Owner | Last Updated
MLS-001 | PRJ-001 | Complete CRM UAT | 2026-08-10 | 2026-08-18 |  | Delayed | Yes | Ahmed Khan | 2026-08-12
MLS-002 | PRJ-001 | Production Go-Live | 2026-09-15 | 2026-09-22 |  | At Risk | Yes | Ahmed Khan | 2026-08-12
MLS-003 | PRJ-002 | ERP User Training Complete | 2026-09-05 | 2026-09-05 |  | On Track | No | Sara Malik | 2026-08-12
MLS-004 | PRJ-002 | ERP Production Go-Live | 2026-11-15 | 2026-11-15 |  | On Track | Yes | Sara Malik | 2026-08-12
MLS-005 | PRJ-003 | Performance Testing Complete | 2026-08-05 | 2026-08-16 |  | Delayed | Yes | Development Lead | 2026-08-12
MLS-006 | PRJ-003 | Mobile App Launch | 2026-08-31 | 2026-09-15 |  | At Risk | Yes | Omar Ali | 2026-08-12
MLS-007 | PRJ-004 | Dashboard Validation Complete | 2026-08-22 | 2026-08-22 |  | On Track | No | BI Lead | 2026-08-12
MLS-008 | PRJ-004 | Analytics Platform Go-Live | 2026-12-01 | 2026-12-01 |  | On Track | Yes | Fatima Noor | 2026-08-12
MLS-009 | PRJ-005 | Hardware Delivery Complete | 2026-08-08 | 2026-08-20 |  | Delayed | Yes | Khalid Hassan | 2026-08-12
MLS-010 | PRJ-005 | Infrastructure Migration Complete | 2026-10-15 | 2026-10-25 |  | At Risk | Yes | Infrastructure Manager | 2026-08-12

## Dependencies
Dependency ID | Project ID | Dependency | Dependency Type | Dependent On | Owner | Required By Date | Status | Impact if Delayed | Escalation Required | Last Updated
DEP-001 | PRJ-001 | CRM production deployment depends on UAT defect closure | Internal | Development Team | Ahmed Khan | 2026-08-18 | At Risk | Production go-live may slip | Yes | 2026-08-12
DEP-002 | PRJ-001 | CRM go-live depends on production environment readiness | Internal | Infrastructure Team | IT Manager | 2026-09-10 | On Track | Deployment cannot proceed | No | 2026-08-12
DEP-003 | PRJ-002 | ERP finance module depends on finance integration defect resolution | Internal | Integration Team | Sara Malik | 2026-08-15 | At Risk | Finance processing and go-live readiness may be affected | Yes | 2026-08-12
DEP-004 | PRJ-003 | Mobile app launch depends on performance testing completion | Internal | Development Team | Omar Ali | 2026-08-16 | Delayed | Mobile app launch may be postponed | Yes | 2026-08-12
DEP-005 | PRJ-003 | Mobile app launch depends on business approval of revised launch date | Governance | Business Owner | Omar Ali | 2026-08-15 | At Risk | Release planning remains blocked | Yes | 2026-08-12
DEP-006 | PRJ-004 | Dashboard validation depends on source data reconciliation | Data | Source System Owners | BI Lead | 2026-08-20 | At Risk | Dashboard accuracy may be compromised | No | 2026-08-12
DEP-007 | PRJ-005 | Infrastructure migration depends on hardware delivery | External Vendor | Hardware Vendor | Khalid Hassan | 2026-08-20 | Delayed | Migration schedule may slip | Yes | 2026-08-12
DEP-008 | PRJ-005 | Network migration depends on approved rollback plan | Internal | Infrastructure Team | Infrastructure Manager | 2026-09-30 | On Track | Service recovery risk increases during migration | No | 2026-08-12