## Actions
Action ID | Project ID | Project | Meeting Title | Meeting Date | Description | Owner | Due Date | Priority | Status | Completion Date | Days Overdue | Escalation Status | Created Date | Last Updated
ACT-002 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Confirm the final migration schedule | Ahmed | 2026-08-07 | Medium | Open |  |  | None | 2026-07-27 | 2026-07-29

## Decisions
Decision ID | Project ID | Project | Meeting Title | Meeting Date | Decision | Decision Date | Decision Owner | Status | Created Date | last updated
DEC-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Business team approved the new customer onboarding process | 2026-07-27 | TBD | Approved | 2026-07-27 | 2026-07-29

## Risks
Risk ID | Project ID | Project | Meeting Title | Meeting Date | Risk Description | Probability | Impact | Mitigation | Risk Owner | Status | Risk Score | Risk Rating | Last Review Date | Next Review Date | Created Date | Last Updated | Risk Title | Risk Key
RSK-002 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | The vendor has confirmed that the production servers may be delivered five days late, which could delay system testing. | Medium | High | Coordinate with vendor to confirm revised delivery date, adjust system testing schedule, and identify temporary test environment options. |  | Open | 6 | High | 2026-08-01 | 2026-08-08 | 2026-08-01 | 2026-08-01 | Vendor production server delivery delay | prj-001-vendor-production-server-delivery-delay
RSK-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | UAT could be delayed if data cleansing is not completed on time | Medium | To be assessed | Mitigation to be defined | TBD | Open | 6 | High | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-29 | Vendor production server delivery delay | prj-002-vendor-production-server-delivery-delay

## Issues
Issue ID | Project ID | Project | Issue Title | Meeting Title | Meeting Date | Issue Description | Owner | Impact | Status | Resolution | Severity | Created Date | Last Updated | Issue Key
ISS-20260801052741-01 | PRJ-001 | CRM Implementation | Finance approval blocking development |  |  | The Finance department has not yet approved the additional integration budget, and development work is currently blocked. |  |  | Open |  | Critical | 2026-08-01 | 2026-08-01 | prj-001-finance-approval-blocking-development
ISS-20260801055157-01 | PRJ-001 | CRM Implementation | Finance approval blocking development |  |  | The Finance department has not yet approved the additional integration budget, and development work is currently blocked. |  |  | Open |  | Critical | 2026-08-01 | 2026-08-01 | prj-001-finance-approval-blocking-development

## Assumptions
Assumption ID | Project ID | Project | Meeting Title | Meeting Date | Validation Result | Assumption Title | Assumption Description | Owner | Due Date | Status | Created Date | Last Updated | Closure Date | Last Review Date | Next Review Date | Assumption Key
ASM-20260801052738-01 | PRJ-001 | CRM Implementation |  |  |  | Customer data migration delivery | The project team assumes that the customer data migration files will be provided by 5 August 2026. |  | 2026-08-05 | Open | 2026-08-01 | 2026-08-01 |  | 2026-08-01 | 2026-08-08 | prj-001-customer-data-migration-delivery
ASM-20260801055151-01 | PRJ-001 | CRM Implementation |  |  |  | Customer data migration delivery | The project team assumes that the customer data migration files will be provided by 5 August 2026. |  | 2026-08-05 | Open | 2026-08-01 | 2026-08-01 |  | 2026-08-01 | 2026-08-08 | prj-001-customer-data-migration-delivery
ASM-20260801055319-01 | PRJ-001 | CRM Implementation |  |  |  | Customer data migration delivery | The project team assumes that the customer data migration files will be provided by 5 August 2026. |  | 2026-08-05 | Open | 2026-08-01 | 2026-08-01 |  | 2026-08-01 | 2026-08-08 | prj-001-customer-data-migration-delivery

## Dependencies
Dependency ID | Project ID | Project | Dependency Title | Dependency Description | Owner | Due Date | Status | Created Date | Last Updated | Last Review Date | Next Review Date | Dependency Key
DEP-20260801052745-01 | PRJ-001 | CRM Implementation | UAT depends on CRM and SAP integration | User acceptance testing depends on completion of the CRM and SAP integration. |  |  | Open | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-08 | prj-001-uat-depends-on-crm-and-sap-integration
DEP-20260801052745-02 | PRJ-001 | CRM Implementation | Infrastructure Manager follow up with vendor | The Infrastructure Manager will follow up with the vendor by 2 August 2026. | Infrastructure Manager | 2026-08-02 | Open | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-08 | prj-001-infrastructure-manager-follow-up-with-vendor
DEP-20260801055849-01 | PRJ-001 | CRM Implementation | UAT depends on CRM and SAP integration | User acceptance testing depends on completion of the CRM and SAP integration. |  |  | Open | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-08 | prj-001-uat-depends-on-crm-and-sap-integration
DEP-20260801055849-02 | PRJ-001 | CRM Implementation | Infrastructure Manager follow up with vendor | The Infrastructure Manager will follow up with the vendor by 2 August 2026. | Infrastructure Manager | 2026-08-02 | Open | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-08 | prj-001-infrastructure-manager-follow-up-with-vendor

## Alert Log
Alert Key | Project ID | Raid ID | Raid Type | Title | Rating | Alert Date | Recipient
prj-001-vendor-production-server-delivery-delay-high | PRJ-001 |  | Risk | Vendor production server delivery delay | High | 2026-08-01T05:27:37.854-04:00 | aziz.syed06@gmail.com
prj-001-vendor-production-server-delivery-delay-high | PRJ-001 |  | Risk | Vendor production server delivery delay | High | 2026-08-01T05:50:23.146-04:00 | aziz.syed06@gmail.com

## Project Health
Assessment ID | Assessment Date | Project ID | Project | Schedule Score | RAID Score | Action Score | Financial Score | Governance Score | Overall Health Score | RAG Status | Previous Score | Score Change | Trend | Critical Override | Top Health Driver 1 | Top Health Driver 2 | Top Health Driver 3 | AI Executive Summary | Recommended Action 1 | Recommended Action 2 | Recommended Action 3 | Management Attention
PHA-PRJ-001-20260811014729 | 2026-08-11 | PRJ-001 | CRM Implementation | 15 | 50 | 50 | 40 | 25 | 36 | Red |  |  |  | TRUE | Schedule (Score 15) — weakest component and flagged by Schedule Critical Override = true | Governance (Score 25) — second weakest component indicating low governance effectiveness | RAID Critical Override = true with 1 Critical Issue — an active critical issue requiring executive attention | Overall project health is Red (Overall Health Score 36) driven by a critically weak schedule and governance shortfalls, with a RAID critical override active. Immediate management controls are required to address the schedule override and the single critical RAID issue. | Address Schedule (Schedule Score 15; Schedule Critical Override = true): Immediate management control required — escalate schedule status to executive management for validation and require a time-bound recovery plan with clear, measurable milestones and direct reporting of progress to management until the schedule condition is resolved. | Address RAID Critical Override and Critical Issue (RAID Critical Override = true; Critical Issues = 1): Immediate management control required — institute an executive-level triage of the critical issue to confirm its classification and mandate documented mitigation/contingency actions and status updates to management until the critical issue is closed or downgraded. | Address Governance (Governance Score 25): Immediate management control required — require a governance review to confirm decision rights, escalation paths and oversight controls are in place and request documented evidence of governance actions or gaps to be reported to management for remedial direction. | Immediate attention is required on the Schedule (Score 15) because Schedule Critical Override is active, and on the RAID Critical Override (true) tied to the single critical issue; additionally, low Governance (Score 25) must be corrected to ensure effective oversight of the above actions.
PHA-PRJ-001-20260811015537 | 2026-08-11 | PRJ-001 | CRM Implementation | 15 | 50 | 50 | 40 | 25 | 36 | Red |  |  |  | TRUE | Schedule (Score 15) — weakest component and flagged by Schedule Critical Override = true | Governance (Score 25) — second weakest component indicating low governance effectiveness | RAID Critical Override = true with 1 Critical Issue — an active critical issue requiring executive attention | Overall project health is Red (Overall Health Score 36) driven by a critically weak schedule and governance shortfalls, with a RAID critical override active. Immediate management controls are required to address the schedule override and the single critical RAID issue. | Address Schedule (Schedule Score 15; Schedule Critical Override = true): Immediate management control required — escalate schedule status to executive management for validation and require a time-bound recovery plan with clear, measurable milestones and direct reporting of progress to management until the schedule condition is resolved. | Address RAID Critical Override and Critical Issue (RAID Critical Override = true; Critical Issues = 1): Immediate management control required — institute an executive-level triage of the critical issue to confirm its classification and mandate documented mitigation/contingency actions and status updates to management until the critical issue is closed or downgraded. | Address Governance (Governance Score 25): Immediate management control required — require a governance review to confirm decision rights, escalation paths and oversight controls are in place and request documented evidence of governance actions or gaps to be reported to management for remedial direction. | Immediate attention is required on the Schedule (Score 15) because Schedule Critical Override is active, and on the RAID Critical Override (true) tied to the single critical issue; additionally, low Governance (Score 25) must be corrected to ensure effective oversight of the above actions.
PHA-PRJ-001-20260811015723 | 2026-08-11 | PRJ-001 | CRM Implementation | 15 | 50 | 50 | 40 | 25 | 36 | Red |  |  |  | TRUE | Schedule (Score 15) — weakest component and flagged by Schedule Critical Override = true | Governance (Score 25) — second weakest component indicating low governance effectiveness | RAID Critical Override = true with 1 Critical Issue — an active critical issue requiring executive attention | Overall project health is Red (Overall Health Score 36) driven by a critically weak schedule and governance shortfalls, with a RAID critical override active. Immediate management controls are required to address the schedule override and the single critical RAID issue. | Address Schedule (Schedule Score 15; Schedule Critical Override = true): Immediate management control required — escalate schedule status to executive management for validation and require a time-bound recovery plan with clear, measurable milestones and direct reporting of progress to management until the schedule condition is resolved. | Address RAID Critical Override and Critical Issue (RAID Critical Override = true; Critical Issues = 1): Immediate management control required — institute an executive-level triage of the critical issue to confirm its classification and mandate documented mitigation/contingency actions and status updates to management until the critical issue is closed or downgraded. | Address Governance (Governance Score 25): Immediate management control required — require a governance review to confirm decision rights, escalation paths and oversight controls are in place and request documented evidence of governance actions or gaps to be reported to management for remedial direction. | Immediate attention is required on the Schedule (Score 15) because Schedule Critical Override is active, and on the RAID Critical Override (true) tied to the single critical issue; additionally, low Governance (Score 25) must be corrected to ensure effective oversight of the above actions.
PHA-PRJ-001-20260811021127 | 2026-08-11 | PRJ-001 | CRM Implementation | 15 | 50 | 50 | 40 | 25 | 36 | Red | 36 | 0 | Stable | TRUE | Schedule — weakest component (Score 15) with Schedule Critical Override = true | Governance — second weakest component (Score 25) reducing decision effectiveness | RAID Critical Override = true with 1 Critical Issue — mandates immediate escalation | Overall health is Red (score 36), driven by a critically weak schedule (score 15) and weak governance (score 25). A RAID critical override is active and there is one critical issue requiring escalation; action capability is the strongest component but only middling (50). | Addressing: Schedule (Score 15) and Schedule Critical Override = true. Immediate management control: management must formally validate and accept the current schedule status, explicitly acknowledge schedule impacts, and authorize the necessary executive-level schedule decisions (trade-offs or acceptances) required to move forward. | Addressing: RAID Critical Override = true and Critical Issues = 1. Immediate management control: management must formally acknowledge the critical issue in the RAID register, decide whether to accept, mitigate, or escalate the issue, and record the chosen resolution/acceptance path so the project has clear executive direction. | Addressing: Governance (Score 25). Immediate management control: management must confirm that governance authorities and escalation pathways are in place and being applied to enable timely executive decisions on the schedule and the RAID critical issue, and require enforcement of those governance controls until stability is restored. | Immediate attention is required to (1) validate and take executive decisions on the schedule under the active Schedule Critical Override, (2) acknowledge and resolve the single critical RAID issue under the RAID Critical Override, and (3) confirm governance adequacy to ensure those decisions are executed.

## Project Alerts
Alert ID | Assessment ID | Project ID | Project | Alert Type | Alert Key | Alert Status | Overall Health Score | Previous Score | Score Change | RAG Status | Critical Override | Sent Date
ALT-PRJ-001-20260811022907 |  | PRJ-001 | CRM Implementation | CRITICAL_OVERRIDE | PRJ-001¦CRITICAL_OVERRIDE | SENT | 36 | 36 | 0 | Red | TRUE | 2026-08-11 02:37

## Schedule
Project ID | Project | Milestone ID | Milestone | Planned Date | Actual Date | Forecast Date | Status | Critical Path | Last Updated
PRJ-001 | CRM Implementation | MS-001 | Requirements Sign-off | 2026-07-20 | 2026-07-20 | 2026-07-20 | Completed | No | 2026-07-20
PRJ-001 | CRM Implementation | MS-002 | CRM-SAP Integration Complete | 2026-08-05 |  | 2026-08-14 | In Progress | Yes | 2026-08-10
PRJ-001 | CRM Implementation | MS-003 | Production Servers Available | 2026-08-07 |  | 2026-08-12 | Delayed | Yes | 2026-08-10
PRJ-001 | CRM Implementation | MS-004 | UAT Start | 2026-08-10 |  | 2026-08-18 | Not Started | Yes | 2026-08-10
PRJ-001 | CRM Implementation | MS-005 | Go-Live | 2026-08-31 |  | 2026-09-07 | Not Started | Yes | 2026-08-10

## Financial
Project ID | Project | Approved Budget | Actual Cost | Forecast at Completion | Budget Variance % | Cost Status | Last Updated
PRJ-001 | CRM Implementation | 500000 | 410000 | 560000 | 12 | Over Budget | 2026-08-10

## Governance
Project ID | Project | Status Report Due Date | Status Report Submitted Date | RAID Review Due Date | RAID Review Completed Date | Steering Committee Due Date | Steering Committee Held Date | Pending Decisions | Mandatory Fields Complete | Last Updated
PRJ-001 | CRM Implementation | 2026-08-09 | 2026-08-10 | 2026-08-08 |  | 2026-08-07 |  | 2 | No | 2026-08-10

## Result
Result from Project 01
Action
Action ID | Project ID | Project | Meeting Title | Meeting Date | Description | Owner | Due Date | Priority | Status | Completion Date | Days Overdue | Escalation Status | Created Date | Last Updated
ACT-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Complete data cleansing for source data | IT team | 2026-08-05 | Medium | Open |  |  | None | 2026-07-27 | 2026-07-29
ACT-002 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Confirm the final migration schedule | Ahmed | 2026-08-07 | Medium | Open |  |  | None | 2026-07-27 | 2026-07-29
Decisions
Decision ID | Project ID | Project | Meeting Title | Meeting Date | Decision | Decision Date | Decision Owner | Status | Created Date | Last Updated
DEC-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Business team approved the new customer onboarding process | 2026-07-27 | TBD | Approved | 2026-07-27 | 2026-07-29
Risk
Risk ID | Project ID | Project | Meeting Title | Meeting Date | Risk Description | Probability | Impact | Mitigation | Risk Owner | Status | Risk Score | Risk Rating | Last Review Date | Next Review Date | Created Date | Last Updated
RSK-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | UAT could be delayed if data cleansing is not completed on time | Medium | To be assessed | Mitigation to be defined | TBD | Open |  |  | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-29
Issue ID
Issue ID | Project ID | Project | Meeting Title | Meeting Date | Issue Description | Owner | Impact | Status | Resolution | Severity | Created Date | Last Updated
ISS-001 | PRJ-001 | CRM Implementation | Weekly Project Status Meeting | 2026-07-27 | Data migration is currently delayed because the source data is not clean | TBD | Data migration delayed | Delayed | Pending Investigation | Medium | 2026-07-27 | 2026-07-29